## Summary (hidden)
AY26-27 Classera Plans ¦ Events Tracker
Live summary from the Events sheet. Every number below is a formula, so it updates as you edit the tracker.
Today | 2026-10-04
Program | Events | Upcoming | Next 14 days | Date TBC | Links Published | Links Missing | Delivered | Registrations | Attendees | Attendance Rate | Avg Satisfaction | Open Flags
Professional Development | 12 | 10 | 1 | 0 | 2 | 10 | 2 | 1095 | 677 | 61.83% | - | 1
Accreditation | 19 | 18 | 1 | 0 | 19 | 0 | 1 | 0 | 0 | - | - | 1
Enrichment Academy | 33 | 31 | 3 | 0 | 12 | 21 | 1 | 1447 | 783 | 54.11% | - | 2
Product Events | 4 | 4 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | - | - | 0
In-Person Events | 12 | 12 | 0 | 11 | 0 | 12 | 0 | 0 | 0 | - | - | 0
Total | 80 | 75 | 5 | 12 | 33 | 47 | 4 | 2542 | 1460 | 57.44% | - | 4
Status pipeline
| Planned | Confirmed | Registration Open | Delivered | Postponed | Cancelled
Events | 46 | 1 | 29 | 4 | 0 | 0
Follow-up flags
Update status | 0 | Event date has passed but Event Status is not Delivered, Postponed or Cancelled
Add link | 1 | Event starts within 14 days (or is running) and has no registration link
Announce | 3 | Event starts within 14 days and the announcement is not Published yet

## Guide (hidden)
How to use this tracker
Source | All 80 events were pulled from plans.classera.com on 1 Oct 2026 (titles match the site wording) (PD plan, Accreditation calendar, Enrichment plan, Product Events, In-Person Events, Full Calendar).
Column colors | Navy headers = plan data from the site. Gold headers (light-yellow cells) = your tracking inputs. Grey headers = formulas, do not type over them.
Daily follow-up | Filter the Events sheet on Action Flag, or check the Follow-up flags block on the Summary sheet.
Event Status | Planned > Confirmed > Registration Open > Delivered. Use Postponed or Cancelled when needed. Past events stay flagged until you set a final status.
Date Status | "Day TBC" rows use the 1st of the month as Start Date and the month end as End Date until the day is confirmed. Update both dates and set Date Status to Confirmed.
Registration Link | Paste the course or short link. Link Status turns Published automatically. Keep it in sync with links.json on the plans site.
Adding events | Type in the first empty row under the table: it extends automatically and the formulas fill down. Use a new Event ID with the program prefix (PD-, ACC-, ENR-, PRD-, INP-).
Dropdown options | Edit the Lists sheet to change the options for Program, Event Status, Announcement Status, Date Status, Delivery Mode and Pricing.
Website | This file also drives plans.classera.com. Upload it to the site repository as events-tracker.xlsx: titles, dates, time, audience, language, partner, pricing, countries, status and registration links update on every page. The page text and design stay in the HTML.
Site Key | Links a row to its card on the website (pd-s03, enr-05, in-person-events-bett-uk...). Do not change existing keys. New rows without a key appear in the Full Calendar only.
Status on the site | Cancelled hides the event from the calendar and marks its card. Postponed marks the card. Delivered shows Completed.
Dashboard | The dashboard at plans.classera.com/tracker/ reads the same file. Keep the header names unchanged. Keep your own versions in OneDrive (v2, v3...) and upload the latest as events-tracker.xlsx.
Example row | PD-S01 shows a complete row: confirmed date, published link and Registration Open status. Fill Owner, Registrations, Attendees and Satisfaction % after delivery.

## Events
Event ID | Program | Track | Event Title (EN) | Event Title (AR) | Partner / Host | Start Date | End Date | Date Status | Month | Semester | Day | Time (KSA) | Audience | Language | Country / Location | Delivery Mode | Pricing | Registration Link | Link Status | Event Status | Announcement Status | Owner | Registrations | Attendees | Attendance Rate | Satisfaction % | Next Action | Due Date | Notes | Timing | Days to Go | Action Flag | Site Key | Title
PD-LW1 | Professional Development | Launch Webinar | Launch Webinar 1: Creativity & Accreditation Plan | الويبينار التعريفي الأول: الإبداع وخطة الاعتماد | PS Training Unit | 2026-09-28 | 2026-09-28 | Confirmed | 2026-09-01 | Semester 1 | Mon | 5:00 PM | Teachers + School Leaders | Arabic | Online - Classera Innovation Platform | Online |  | https://sh.classera.com/EPD | Published | Delivered | Published |  | 543 | 426 | 78.45% |  |  |  |  | Past
ENR-LW2 | Enrichment Academy | Launch Webinar | Launch Webinar 2: Enrichment Programs Plan | الويبينار التعريفي الثاني: خطة البرامج الإثرائية | PS Training Unit | 2026-09-29 | 2026-09-29 | Confirmed | 2026-09-01 | Semester 1 | Tue | 10:00 AM | Teachers + School Leaders | Arabic | Online - Classera Innovation Platform | Online |  | https://sh.classera.com/Enrich | Published | Delivered | Published |  | 116 | 37 | 31.9% |  |  |  |  | Past
PD-S01 | Professional Development | Classera LMS | Academic Year Kickoff & Classera LMS Updates — New Features & Release Highlights | انطلاقة العام الأكاديمي وتحديثات نظام كلاسيرا — المزايا الجديدة وأبرز الإصدارات | Classera | 2026-09-30 | 2026-09-30 | Confirmed | 2026-09-01 | Semester 1 | Wed | 5:00 PM | All LMS Users | Arabic | Online - Classera Innovation Platform | Online |  | https://sh.classera.com/v17unlocked | Published | Delivered | Published |  | 552 | 251 | 45.47% |  |  |  |  | Past |  |  | pd-s01
PD-S02 | Professional Development | Intel SFI | Intel Skills for Innovation (SFI) Webinar 1 — AI Professional Development | Intel Skills for Innovation — التطوير المهني في الذكاء الاصطناعي (1) | Intel | 2026-10-14 | 2026-10-14 | Confirmed | 2026-10-01 | Semester 1 | Wed | 5:00 PM | Teachers | English | Online - Classera Innovation Platform | Online |  |  | Missing | Confirmed | Not started | [8 empty] | Next 14 days | 10 | Add link | pd-s02
PD-S03 | Professional Development | EdTech Partner | From Explanation to Experiment: Transforming Science Teaching with Virtual Labs | من الشرح إلى التجربة: تحويل تدريس العلوم بالمعامل الافتراضية | Vlaby | 2026-10-28 | 2026-10-28 | Confirmed | 2026-10-01 | Semester 1 | Wed | 5:00 PM | Teachers & Supervisors | Arabic | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Next 45 days | 24 |  | pd-s03
PD-S04 | Professional Development | EdTech Partner | Empower Every Learner | تمكين كل متعلم | University Startup | 2026-11-11 | 2026-11-11 | Confirmed | 2026-11-01 | Semester 1 | Wed | 5:00 PM | Teachers & Supervisors | English | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Next 45 days | 38 |  | pd-s04
PD-S05 | Professional Development | Intel SFI | Intel Skills for Innovation (SFI) Webinar 2 — AI Professional Development | Intel Skills for Innovation — التطوير المهني في الذكاء الاصطناعي (2) | Intel | 2026-12-09 | 2026-12-09 | Confirmed | 2026-12-01 | Semester 1 | Wed | 5:00 PM | Teachers | English | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 66 |  | pd-s05
PD-S06 | Professional Development | EdTech Partner | How do AI-powered solutions measure adaptive-learning outcomes? | كيف تقيس الحلول المدعومة بالذكاء الاصطناعي مخرجات التعلم التكيفي؟ | AILA | 2026-12-23 | 2026-12-23 | Confirmed | 2026-12-01 | Semester 1 | Wed | 5:00 PM | Teachers & Supervisors | Arabic | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 80 |  | pd-s06
PD-S07 | Professional Development | Intel SFI | Intel Skills for Innovation (SFI) Webinar 3 — AI Professional Development | Intel Skills for Innovation — التطوير المهني في الذكاء الاصطناعي (3) | Intel | 2027-03-17 | 2027-03-17 | Confirmed | 2027-03-01 | Semester 2 | Wed | 5:00 PM | Teachers | English | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 164 |  | pd-s07
PD-S08 | Professional Development | Classera LMS | Classera LMS Updates | تحديثات نظام كلاسيرا | Classera Product Team | 2027-03-31 | 2027-03-31 | Confirmed | 2027-03-01 | Semester 2 | Wed | 5:00 PM | All LMS Users | Arabic | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 178 |  | pd-s08
PD-S09 | Professional Development | EdTech Partner | Technology in Education Webinar Series — Session 4 | سلسلة تقنيات التعليم — الجلسة الرابعة |  | 2027-04-07 | 2027-04-07 | Confirmed | 2027-04-01 | Semester 2 | Wed | 5:00 PM | Teachers & Supervisors |  | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 185 |  | pd-s09
PD-S10 | Professional Development | EdTech Partner | Technology in Education Webinar Series — Session 5 | سلسلة تقنيات التعليم — الجلسة الخامسة |  | 2027-04-21 | 2027-04-21 | Confirmed | 2027-04-01 | Semester 2 | Wed | 5:00 PM | Teachers & Supervisors |  | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 199 |  | pd-s10
PD-S11 | Professional Development | EdTech Partner | Technology in Education Webinar Series — Session 6 | سلسلة تقنيات التعليم — الجلسة السادسة |  | 2027-05-05 | 2027-05-05 | Confirmed | 2027-05-01 | Semester 2 | Wed | 5:00 PM | Teachers & Supervisors |  | Online - Classera Innovation Platform | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 213 |  | pd-s11
ACC-01 | Accreditation | Exam Window | Accreditation Exam Window: September 2026 (Period 1) | فترة اختبارات الاعتماد: سبتمبر 2026 (الفترة 1) | Classera & Intel | 2026-09-21 | 2026-09-27 | Confirmed | 2026-09-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Delivered | Published | [8 empty] | Past
ACC-02 | Accreditation | Exam Window | Accreditation Exam Window: October 2026 (Period 1) | فترة اختبارات الاعتماد: أكتوبر 2026 (الفترة 1) | Classera & Intel | 2026-10-05 | 2026-10-11 | Confirmed | 2026-10-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Next 14 days | 1 | Announce
ACC-03 | Accreditation | Exam Window | Accreditation Exam Window: October 2026 (Period 2) | فترة اختبارات الاعتماد: أكتوبر 2026 (الفترة 2) | Classera & Intel | 2026-10-19 | 2026-10-25 | Confirmed | 2026-10-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Next 45 days | 15
ACC-04 | Accreditation | Exam Window | Accreditation Exam Window: November 2026 (Period 1) | فترة اختبارات الاعتماد: نوفمبر 2026 (الفترة 1) | Classera & Intel | 2026-11-09 | 2026-11-15 | Confirmed | 2026-11-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Next 45 days | 36
ACC-05 | Accreditation | Exam Window | Accreditation Exam Window: November 2026 (Period 2) | فترة اختبارات الاعتماد: نوفمبر 2026 (الفترة 2) | Classera & Intel | 2026-11-23 | 2026-11-29 | Confirmed | 2026-11-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 50
ACC-06 | Accreditation | Exam Window | Accreditation Exam Window: December 2026 (Period 1) | فترة اختبارات الاعتماد: ديسمبر 2026 (الفترة 1) | Classera & Intel | 2026-12-07 | 2026-12-13 | Confirmed | 2026-12-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 64
ACC-07 | Accreditation | Exam Window | Accreditation Exam Window: December 2026 (Period 2) | فترة اختبارات الاعتماد: ديسمبر 2026 (الفترة 2) | Classera & Intel | 2026-12-21 | 2026-12-27 | Confirmed | 2026-12-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 78
ACC-08 | Accreditation | Exam Window | Accreditation Exam Window: January 2027 (Period 1) | فترة اختبارات الاعتماد: يناير 2027 (الفترة 1) | Classera & Intel | 2027-01-04 | 2027-01-10 | Confirmed | 2027-01-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 92
ACC-09 | Accreditation | Exam Window | Accreditation Exam Window: January 2027 (Period 2) | فترة اختبارات الاعتماد: يناير 2027 (الفترة 2) | Classera & Intel | 2027-01-18 | 2027-01-24 | Confirmed | 2027-01-01 | Semester 1 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 106
ACC-10 | Accreditation | Exam Window | Accreditation Exam Window: February 2027 (Period 1) | فترة اختبارات الاعتماد: فبراير 2027 (الفترة 1) | Classera & Intel | 2027-02-08 | 2027-02-14 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 127
ACC-11 | Accreditation | Exam Window | Accreditation Exam Window: February 2027 (Period 2) | فترة اختبارات الاعتماد: فبراير 2027 (الفترة 2) | Classera & Intel | 2027-02-22 | 2027-02-28 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 141
ACC-12 | Accreditation | Exam Window | Accreditation Exam Window: March 2027 (Period 1) | فترة اختبارات الاعتماد: مارس 2027 (الفترة 1) | Classera & Intel | 2027-03-08 | 2027-03-14 | Confirmed | 2027-03-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 155
ACC-13 | Accreditation | Exam Window | Accreditation Exam Window: March 2027 (Period 2) | فترة اختبارات الاعتماد: مارس 2027 (الفترة 2) | Classera & Intel | 2027-03-22 | 2027-03-28 | Confirmed | 2027-03-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 169
ACC-14 | Accreditation | Exam Window | Accreditation Exam Window: April 2027 (Period 1) | فترة اختبارات الاعتماد: أبريل 2027 (الفترة 1) | Classera & Intel | 2027-04-05 | 2027-04-11 | Confirmed | 2027-04-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 183
ACC-15 | Accreditation | Exam Window | Accreditation Exam Window: April 2027 (Period 2) | فترة اختبارات الاعتماد: أبريل 2027 (الفترة 2) | Classera & Intel | 2027-04-19 | 2027-04-25 | Confirmed | 2027-04-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 197
ACC-16 | Accreditation | Exam Window | Accreditation Exam Window: May 2027 (Period 1) | فترة اختبارات الاعتماد: مايو 2027 (الفترة 1) | Classera & Intel | 2027-05-03 | 2027-05-09 | Confirmed | 2027-05-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 211
ACC-17 | Accreditation | Exam Window | Accreditation Exam Window: May 2027 (Period 2) | فترة اختبارات الاعتماد: مايو 2027 (الفترة 2) | Classera & Intel | 2027-05-24 | 2027-05-30 | Confirmed | 2027-05-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 232
ACC-18 | Accreditation | Exam Window | Accreditation Exam Window: June 2027 (Period 1) | فترة اختبارات الاعتماد: يونيو 2027 (الفترة 1) | Classera & Intel | 2027-06-07 | 2027-06-13 | Confirmed | 2027-06-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 246
ACC-19 | Accreditation | Exam Window | Accreditation Exam Window: June 2027 (Period 2) | فترة اختبارات الاعتماد: يونيو 2027 (الفترة 2) | Classera & Intel | 2027-06-21 | 2027-06-27 | Confirmed | 2027-06-01 | Semester 2 | Mon |  | Educators (Teachers, School Leaders, System Managers) |  | Online - Accreditation Platform | Online |  | https://accreditation.classera.com/ | Published | Registration Open | Not started | [8 empty] | Later | 260
ENR-01 | Enrichment Academy | National & Awareness | Saudi National Day Activities | فاعليات اليوم الوطني | Enrichment Academy | 2026-09-21 | 2026-09-21 | Confirmed | 2026-09-01 | Semester 1 | Mon |  | All grades |  | Saudi Arabia | Online | Free | https://sh.classera.com/NationalDay | Published | Registration Open | Published |  | 1221 | 746 | 61.1% |  |  |  |  | Past |  | Announce | enr-01
ENR-02 | Enrichment Academy | National & Awareness | World Teachers' Day | يوم المعلم | Enrichment Academy | 2026-10-05 | 2026-10-05 | Confirmed | 2026-10-01 | Semester 1 | Mon |  | Teachers |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Free | https://iacademy.classera.com/lectures-list/?course_title=يوم%20المعلم%2026-27&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc0MzYifQ | Published | Registration Open | Published |  | 110 | 0 | 0% |  |  |  |  | Next 14 days | 1 |  | enr-02
ENR-03 | Enrichment Academy | National & Awareness | October 6 Victory Celebration | فعاليات نصر 6 أكتوبر | Enrichment Academy | 2026-10-06 | 2026-10-06 | Confirmed | 2026-10-01 | Semester 1 | Tue |  | All grades |  | Egypt | Online | Free | https://iacademy.classera.com/lectures-list/?course_title=فاعليات%20%20نصر%20اكتوبر%2026-27&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjQwNDMifQ | Published | Registration Open | Published | [8 empty] | Next 14 days | 2 |  | enr-03
ENR-04 | Enrichment Academy | Skill Courses | Mobile App Programming | مهارات برمجة تطبيقات الجوال | Enrichment Academy | 2026-10-12 | 2026-10-12 | Confirmed | 2026-10-01 | Semester 1 | Mon |  | Middle & Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) | https://iacademy.classera.com/lectures-list/?course_title=مهارات%20برمجة%20تطبيقات%20الجوال%2026-27&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc4MzIifQ | Published | Registration Open | Not started | [8 empty] | Next 14 days | 8 | Announce | enr-04
ENR-05 | Enrichment Academy | Skill Courses | Digital Art Fundamentals | اساسيات الرسم الرقمي - Basics Of Digital Art | Enrichment Academy | 2026-10-19 | 2026-10-19 | Confirmed | 2026-10-01 | Semester 1 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Free |  | Missing | Planned | Not started | [8 empty] | Next 45 days | 15 |  | enr-05
ENR-06 | Enrichment Academy | National & Awareness | World Savings Day | يوم الادخار العالمي | Enrichment Academy | 2026-10-26 | 2026-10-26 | Confirmed | 2026-10-01 | Semester 1 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Free | https://iacademy.classera.com/lectures-list/?course_title=27-26%20يوم%20الادخار%20العالمي&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc4MzMifQ | Published | Registration Open | Not started | [8 empty] | Next 45 days | 22 |  | enr-06
ENR-07 | Enrichment Academy | Skill Courses | Programming Fundamentals | اساسيات البرمجة | Enrichment Academy | 2026-11-02 | 2026-11-02 | Confirmed | 2026-11-01 | Semester 1 | Mon |  | Elementary & Middle |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Free | https://iacademy.classera.com/lectures-list/?course_title=اساسيات%20البرمجة%2026-27&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc4MzQifQ | Published | Registration Open | Not started | [8 empty] | Next 45 days | 29 |  | enr-07
ENR-08 | Enrichment Academy | Skill Courses | Roblox Programming | دورة مهارات برمجة الروبلوكس | Enrichment Academy | 2026-11-09 | 2026-11-09 | Confirmed | 2026-11-01 | Semester 1 | Mon |  | Middle |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Free | https://iacademy.classera.com/lectures-list/?course_title=26-27دورة%20مهارات%20برمجة%20الروبلوكس&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc4MzUifQ | Published | Registration Open | Not started | [8 empty] | Next 45 days | 36 |  | enr-08
ENR-09 | Enrichment Academy | Skill Courses | Arduino Skills | مهارات الأردوينو | Enrichment Academy | 2026-11-16 | 2026-11-16 | Confirmed | 2026-11-01 | Semester 1 | Mon |  | Middle & Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) |  | Missing | Planned | Not started | [8 empty] | Next 45 days | 43 |  | enr-09
ENR-10 | Enrichment Academy | Skill Courses | Internet of Things | مهارات انترنيت الاشياء | Enrichment Academy | 2026-11-23 | 2026-11-23 | Confirmed | 2026-11-01 | Semester 1 | Mon |  | Middle & Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) | https://iacademy.classera.com/lectures-list/?course_title=26-27%20مهارات%20انترنيت%20الاشياء&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc4MzYifQ | Published | Registration Open | Not started | [8 empty] | Later | 50 |  | enr-10
ENR-11 | Enrichment Academy | National & Awareness | Riyali Financial Literacy Program | البرنامج ريالي للوعي المالي | Enrichment Academy | 2026-11-30 | 2026-11-30 | Confirmed | 2026-11-01 | Semester 1 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored | https://iacademy.classera.com/lectures-list/?course_title=26-27%20البرنامج%20ريالي%20للوعي%20المالي&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc4MzcifQ | Published | Registration Open | Not started | [8 empty] | Later | 57 |  | enr-11
ENR-12 | Enrichment Academy | Skill Courses | Python Programming | البرمجة بلغة بايثون | Enrichment Academy | 2026-12-07 | 2026-12-07 | Confirmed | 2026-12-01 | Semester 1 | Mon |  | Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) | https://iacademy.classera.com/lectures-list/?course_title=البرمجة%20بلغة%20بايثون%20%2026-27&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc4MzgifQ | Published | Registration Open | Not started | [8 empty] | Later | 64 |  | enr-12
ENR-13 | Enrichment Academy | Skill Courses | Cybersecurity Skills | مهارات برمجية - الأمان الالكتروني | Enrichment Academy | 2026-12-14 | 2026-12-14 | Confirmed | 2026-12-01 | Semester 1 | Mon |  | Middle & Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) | https://iacademy.classera.com/lectures-list/?course_title=مهارات%20برمجية%20-%20الأمان%20الالكتروني%2026-27&course_type=1&c=eyJjb3Vyc2VfaWQiOiIxMjc4MzkifQ | Published | Registration Open | Not started | [8 empty] | Later | 71 |  | enr-13
ENR-14 | Enrichment Academy | Skill Courses | Entrepreneurship | ريادة الأعمال | Enrichment Academy | 2026-12-21 | 2026-12-21 | Confirmed | 2026-12-01 | Semester 1 | Mon |  | Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) |  | Missing | Planned | Not started | [8 empty] | Later | 78 |  | enr-14
ENR-15 | Enrichment Academy | Skill Courses | AI Skills | مهارات الذكاء الاصطناعي | Enrichment Academy | 2027-02-01 | 2027-02-01 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | Middle & Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) |  | Missing | Planned | Not started | [8 empty] | Later | 120 |  | enr-15
ENR-16 | Enrichment Academy | Competitions | Challenge Competition — Question 1 | مسابقة التحدي — السؤال الأول | Enrichment Academy | 2027-02-08 | 2027-02-08 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 127 |  | enr-16
ENR-17 | Enrichment Academy | National & Awareness | Saudi Founding Day Activities | فعاليات يوم التأسيس | Enrichment Academy | 2027-02-15 | 2027-02-15 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia | Online | Free |  | Missing | Planned | Not started | [8 empty] | Later | 134 |  | enr-17
ENR-18 | Enrichment Academy | Competitions | Challenge Competition — Question 2 | مسابقة التحدي — السؤال الثاني | Enrichment Academy | 2027-02-15 | 2027-02-15 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 134 |  | enr-18
ENR-19 | Enrichment Academy | Competitions | Classera Hackathon — Launch | انطلاق هاكثون كلاسيرا | Enrichment Academy | 2027-02-15 | 2027-02-15 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 134 |  | enr-19
ENR-20 | Enrichment Academy | Competitions | Challenge Competition — Question 3 | مسابقة التحدي — السؤال الثالث | Enrichment Academy | 2027-02-22 | 2027-02-22 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 141 |  | enr-20
ENR-21 | Enrichment Academy | Competitions | Challenge Competition — Question 4 | مسابقة التحدي — السؤال الرابع | Enrichment Academy | 2027-03-01 | 2027-03-01 | Confirmed | 2027-03-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 148 |  | enr-21
ENR-22 | Enrichment Academy | Competitions | Challenge Competition — Question 5 | مسابقة التحدي — السؤال الخامس | Enrichment Academy | 2027-03-08 | 2027-03-08 | Confirmed | 2027-03-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 155 |  | enr-22
ENR-23 | Enrichment Academy | Skill Courses | Robot Programming — Beginner | برمجة الروبوت - المستوى المبتدئ | Enrichment Academy | 2027-03-22 | 2027-03-22 | Confirmed | 2027-03-01 | Semester 2 | Mon |  | Middle |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Free |  | Missing | Planned | Not started | [8 empty] | Later | 169 |  | enr-23
ENR-24 | Enrichment Academy | Skill Courses | Robot Programming — Advanced | مهارات برمجة الروبوت - المستوى المتقدم | Enrichment Academy | 2027-03-29 | 2027-03-29 | Confirmed | 2027-03-01 | Semester 2 | Mon |  | Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) |  | Missing | Planned | Not started | [8 empty] | Later | 176 |  | enr-24
ENR-25 | Enrichment Academy | Skill Courses | Global Robotics Competition Prep | التهيئة لمسابقات الروبوت العالمية | Enrichment Academy | 2027-04-05 | 2027-04-05 | Confirmed | 2027-04-01 | Semester 2 | Mon |  | Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) |  | Missing | Planned | Not started | [8 empty] | Later | 183 |  | enr-25
ENR-26 | Enrichment Academy | Skill Courses | C++ Programming | مهارات برمجية - البرمجة بلغة C+ | Enrichment Academy | 2027-04-12 | 2027-04-12 | Confirmed | 2027-04-01 | Semester 2 | Mon |  | Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) |  | Missing | Planned | Not started | [8 empty] | Later | 190 |  | enr-26
ENR-27 | Enrichment Academy | Skill Courses | Scratch Programming | البرمجة بلغة سكراتش - Scratch | Enrichment Academy | 2027-04-19 | 2027-04-19 | Confirmed | 2027-04-01 | Semester 2 | Mon |  | Elementary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Free |  | Missing | Planned | Not started | [8 empty] | Later | 197 |  | enr-27
ENR-28 | Enrichment Academy | Competitions | National Challenge — Launch | التحدي الوطني — الانطلاق | Enrichment Academy | 2027-04-19 | 2027-04-19 | Confirmed | 2027-04-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 197 |  | enr-28
ENR-29 | Enrichment Academy | Skill Courses | Web Design | تصميم مواقع الانترنت | Enrichment Academy | 2027-04-26 | 2027-04-26 | Confirmed | 2027-04-01 | Semester 2 | Mon |  | Secondary |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Paid (Secondary) |  | Missing | Planned | Not started | [8 empty] | Later | 204 |  | enr-29
ENR-30 | Enrichment Academy | Competitions | Classera Hackathon — Final Stage | المرحلة النهائية لهاكثون كلاسيرا | Enrichment Academy | 2027-05-10 | 2027-05-10 | Confirmed | 2027-05-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 218 |  | enr-30
ENR-31 | Enrichment Academy | National & Awareness | Jordan National Day | اليوم الوطني الأردني | Enrichment Academy | 2027-05-24 | 2027-05-24 | Confirmed | 2027-05-01 | Semester 2 | Mon |  | All grades |  | Jordan | Online | Free |  | Missing | Planned | Not started | [8 empty] | Later | 232 |  | enr-31
ENR-32 | Enrichment Academy | Competitions | National Challenge — Results | التحدي الوطني — إعلان النتائج | Enrichment Academy | 2027-06-14 | 2027-06-14 | Confirmed | 2027-06-01 | Semester 2 | Mon |  | All grades |  | Saudi Arabia, Egypt, Jordan, Other countries | Online | Sponsored |  | Missing | Planned | Not started | [8 empty] | Later | 253 |  | enr-32
PRD-01 | Product Events | Services Introduction | Services introduction session | لقاء تعريفي بالخدمات | EduMalls X + C-Inspire | 2026-10-26 | 2026-10-26 | Confirmed | 2026-10-01 | Semester 1 | Mon |  | Teaching staff |  |  | Online |  |  | Missing | Planned | Not started | [8 empty] | Next 45 days | 22 |  | product-events-intro-services
PRD-02 | Product Events | Offers Campaign | Saudi Founding Day offers | عروض يوم التأسيس السعودي | EduMalls X + C-Inspire | 2027-02-01 | 2027-02-01 | Confirmed | 2027-02-01 | Semester 2 | Mon |  | Teaching staff |  |  | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 120 |  | product-events-founding-day
PRD-03 | Product Events | Product Launch | Launch of the education resource management system | إطلاق نظام إدارة الموارد للمؤسسات التعليمية | C-Smarx | 2027-02-01 | 2027-02-28 | Day TBC | 2027-02-01 | Semester 2 | TBC |  | Administration & finance |  |  | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 120 |  | product-events-csmarks-launch
PRD-04 | Product Events | Offers Campaign | End-of-year offers | عروض نهاية العام | EduMalls X + C-Inspire | 2027-04-20 | 2027-04-20 | Confirmed | 2027-04-01 | Semester 2 | Tue |  | Teaching staff |  |  | Online |  |  | Missing | Planned | Not started | [8 empty] | Later | 198 |  | product-events-year-end-offers
INP-01 | In-Person Events | Classera Forum | Classera Education Forum — Kuwait | ملتقى كلاسيرا للتعليم — الكويت | Hosted by Classera | 2026-12-01 | 2026-12-31 | Day TBC | 2026-12-01 | Semester 1 | TBC |  |  |  | Kuwait | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 58 |  | in-person-events-forum-kw
INP-02 | In-Person Events | Classera Forum | Classera Education & Training Forum — existing clients | ملتقى كلاسيرا للتعليم والتدريب — للعملاء الحاليين | Hosted by Classera | 2026-12-01 | 2026-12-31 | Day TBC | 2026-12-01 | Semester 1 | TBC |  |  |  | Saudi Arabia | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 58 |  | in-person-events-forum-ksa-existing
INP-03 | In-Person Events | International Conference & Expo | Bett UK | مؤتمر ومعرض بيت البريطاني Bett UK | Classera is taking part | 2027-01-01 | 2027-01-31 | Day TBC | 2027-01-01 | Semester 1 | TBC |  |  |  | London, United Kingdom | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 89 |  | in-person-events-bett-uk
INP-04 | In-Person Events | Seasonal Activities | Classera Ramadan activities | فعاليات كلاسيرا الرمضانية | Hosted by Classera | 2027-02-01 | 2027-02-28 | Day TBC | 2027-02-01 | Semester 2 | TBC |  |  |  | Across the region | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 120 |  | in-person-events-ramadan
INP-05 | In-Person Events | InnoXera | InnoXera — Oman | إنوكسيرا InnoXera — عُمان | Classera is taking part | 2027-03-01 | 2027-03-31 | Day TBC | 2027-03-01 | Semester 2 | TBC |  |  |  | Oman | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 148 |  | in-person-events-innoxera-om
INP-06 | In-Person Events | InnoXera | InnoXera — Bahrain | إنوكسيرا InnoXera — البحرين | Classera is taking part | 2027-03-01 | 2027-03-31 | Day TBC | 2027-03-01 | Semester 2 | TBC |  |  |  | Bahrain | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 148 |  | in-person-events-innoxera-bh
INP-07 | In-Person Events | Classera Forum | Classera Education Forum — Egypt | ملتقى كلاسيرا للتعليم — مصر | Hosted by Classera | 2027-04-01 | 2027-04-30 | Day TBC | 2027-04-01 | Semester 2 | TBC |  |  |  | Egypt | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 179 |  | in-person-events-forum-eg
INP-08 | In-Person Events | Classera Forum | Classera Education Forum — new clients | ملتقى كلاسيرا للتعليم — للعملاء الجدد | Hosted by Classera | 2027-04-01 | 2027-04-30 | Day TBC | 2027-04-01 | Semester 2 | TBC |  |  |  | Saudi Arabia | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 179 |  | in-person-events-forum-ksa-new
INP-09 | In-Person Events | InnoXera | InnoXera — Saudi Arabia | إنوكسيرا InnoXera — السعودية | Classera is taking part | 2027-04-01 | 2027-04-30 | Day TBC | 2027-04-01 | Semester 2 | TBC |  |  |  | Saudi Arabia | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 179 |  | in-person-events-innoxera-sa
INP-10 | In-Person Events | International Conference & Expo | Classera at HCI + EDGEx | مشاركة كلاسيرا في HCI + EDGEx | Classera is taking part | 2027-04-12 | 2027-04-13 | Confirmed | 2027-04-01 | Semester 2 | Mon |  |  |  |  | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 190 |  | in-person-events-hci-edgex
INP-11 | In-Person Events | International Conference & Expo | Education World Forum (EWF) — London | مؤتمر منتدى التعليم العالمي EWF — لندن | Classera is taking part | 2027-05-01 | 2027-05-31 | Day TBC | 2027-05-01 | Semester 2 | TBC |  |  |  | London, United Kingdom | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 209 |  | in-person-events-ewf-london
INP-12 | In-Person Events | InnoXera | InnoXera — Qatar | إنوكسيرا InnoXera — قطر | Classera is taking part | 2027-05-01 | 2027-05-31 | Day TBC | 2027-05-01 | Semester 2 | TBC |  |  |  | Qatar | In-person |  |  | Missing | Planned | Not started | [8 empty] | Later | 209 |  | in-person-events-innoxera-qa
Formulas:
Month = IF([Start Date]="","",DATE(YEAR([Start Date]),MONTH([Start Date]),1))
Timing = IF([Start Date]="","",IF([End Date]<TODAY(),"Past",IF([Start Date]<=TODAY(),"In progress",IF([Start Date]-TODAY()<=14,"Next 14 days",IF([Start Date]-TODAY()<=45,"Next 45 days","Later")))))
Days to Go = IF([Start Date]="","",IF([End Date]<TODAY(),"",[Start Date]-TODAY()))

## Lists (hidden)
Program | Event Status | Announcement Status | Date Status | Delivery Mode | Pricing
Professional Development | Planned | Not started | Confirmed | Online | Free
Accreditation | Confirmed | Drafted | Day TBC | In-person | Paid (Secondary)
Enrichment Academy | Registration Open | In review | Month TBC | Hybrid | Sponsored
Product Events | Delivered | Approved |  |  | Paid
In-Person Events | Postponed | Published
Cancelled

## Off-Periods (hidden)
From | To | Off-Period (EN) | Off-Period (AR) | Country | Days
2026-09-23 | 2026-09-26 | KSA National Day | اليوم الوطني السعودي | Saudi Arabia | 4
2026-11-20 | 2026-11-28 | KSA Autumn Break | إجازة الخريف | Saudi Arabia | 9
2027-01-02 | 2027-01-08 | Egypt exam-prep buffer | فترة الاستعداد للامتحانات | Egypt | 7
2027-01-08 | 2027-01-16 | KSA Mid-year Break | إجازة منتصف العام | Saudi Arabia | 9
2027-01-09 | 2027-01-21 | Egypt Term-1 Exams | امتحانات الفصل الأول | Egypt | 13
2027-01-23 | 2027-02-04 | Egypt Mid-year Break | إجازة منتصف العام | Egypt | 13
2027-02-19 | 2027-02-22 | KSA Founding Day | يوم التأسيس السعودي | Saudi Arabia | 4
2027-02-26 | 2027-03-13 | KSA Eid al-Fitr Break | إجازة عيد الفطر | Saudi Arabia | 16
2027-05-07 | 2027-05-22 | KSA Eid al-Adha Break | إجازة عيد الأضحى | Saudi Arabia | 16
2027-05-22 | 2027-05-27 | Egypt End-of-Year Exams | امتحانات نهاية العام | Egypt | 6
Source: plans.classera.com Full Calendar (KSA and Egypt school calendars). No sessions are scheduled inside these periods.